## Sheet1
HabitLens - Major Project - Activity Log Book
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-10-01 | PROJECT IDEATION AND TOPIC SELECTION | Everyone came up with Ideas that could have been the focus of our project and got them reviewd from our Supervisor. Unfortunately none of them were good enough to be selected. | COMING UP WITH MORE VIABLE IDEAS FOR THE PROJECT
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-10-08 | FURTHER PROJECT IDEATION AND TOPIC SELECTION | Everyone came up with Ideas that could have been the focus of our project and got them reviewd from our Supervisor like Stock Market Predictor, Weather Predictor, Receipe Predictor using present Food Items, Automated Financial Fraud detection System | CONDUCTING RESEARCH ON THE TOPICS SELECTED IN THE WEEK
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-10-15 | INDIVIDUAL RESEARCH REGARDING THE VARIOUS TOPICS MENTIONED BEFORE TO DECIDE THE ONE WITH THE MOST POTENTIAL FOR THE PROJECT | CLUBBING THE RESEARCH TOGETHER IN ORDER TO FIND MAXIMUM INDIVIDUAL POTENTIAL | CONDUCTING RESEARCH ON THE VIABILITY AND PRACTICALITY OF THE TOPICS IN THE REAL WORLD
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-10-22 | RESEARCH REGARDING THE VIABILITY IN THE REAL WORLD | Unfortunately many of the above topics had shortcomings and similar programs already in implementation. | DUE TO ABOVE FLAWS A NEW PROJECT TOPIC HAS TO BE SEARCHED
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-10-29 | individually a number of topics were searched for but early on in the week 1 particular topic clicked with all of us so we decided to go further with it. | We got this topic of ours approved by our mentor. | Finding previous Research pepers that support this topic and ones that could be further built upon.
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-11-05 | WE INDIVIDUALLY FOUND SEVERAL RESEARCH PAPERS THAT SUPPORTED THIS IDEAS THAT COULD BE FURTHER BUILT UPON | We went through each others research and disected the best ones that could be the most beneficial to the project | We plan to focus on the Report Format and specialize our research for this project regarding the Literary Survey and finding the Need for the product.
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-11-12 | Once our project was approved and we got the green light Divyam and Dev focused on the Specialized survey for the topic while Tanay and Aayush focused on answering the need of the product that we would eventually develop. | As mentioned the Survey and the Need for the product were counducted and presented to the supervisor. | We plan to hoan in on the exact product problem formulation and extraction of all details as to how we would go about the process.
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-11-19 | All of us tried to answers all the remaining question regarding the Project Design and our expected implementation of the project | The exact problem was formulated along with the Product Objectives, Applications, Novelty and its scope in the real world. | All the work that we have conducted in the previous weeks has to be PRESENTED IN THE FORM OF A PPT PRESENTATION TO OUR GUIDE AND REVIEWER.
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004210034 | DIVYAM DEDHIA | LYNETTE MAAM | 2024-11-25 | All of us collectively worked upon the PRESENTATION that was to bepresented in the Week | PROJECT IDEA PRESENTED | Next week look for the Design of the project and the Ideas for its Implementation
2 | 60004210062 | DEV PATEL
3 | 60004210064 | AAYUSH BHAGAT
4 | 60004210035 | TANAY PARIKH